## Turnkey release
|  |  |  | Production Order Description | [12 empty] | Client Ids With Special Requirements | [5 empty] | No.
|  |  |  | Number: Q64307A1_T1 |  |  |  |  | Issued by: |  | Eyoel | [5 empty] | 50964 | [5 empty] | Yes, see the requirement above for details.
[5 empty] | 2019-08-23 |  |  |  | Ver: 01 | [7 empty] | 51099 | 2019-08-23 | 17
General Information |  |  |  | Project Co-odinator |  |  |  |  | Flora | [7 empty] | 51033 | 2019-09-09
51001
1.Project Name: | SensorPCB_TGS2xxx_V1 | [8 empty] | 7.Ordered Date: |  |  | 2019-08-23 |  |  |  | 50873 |  |  | 0
2.Gerber received date: | SensorPCB_TGS2xxx_V1_2019_08_20 | [8 empty] | 8.Customer ID: |  |  | 52940 |  |  |  | 51262 | 0 |  | 51457 | 0
[18 empty] | 2 |  | 51480 | 0
3.DFM Check: | Yes | [8 empty] | 9.Repeated order: |  |  | No |  |  |  |  | 0 |  | 51506 | 0
[20 empty] | 51919 | 0
4.PCBA Shipment | 1st | 30 | 2nd | 0 | 3rd |  | 4th |  |  | 10.PCBA Ordered: |  |  | 30 | PCS | [5 empty] | 51531 | 0
[20 empty] | 51594 | 0
5.Bare PCB shipmt | 1st | 0 | 2nd | 0 | 3rd |  | 4th |  |  | 11.Customer PO |  |  | 997-007 | [6 empty] | 51803 | 0
[20 empty] | 52158 | 0
6.Shipment date: | 2019-09-09 | [8 empty] | 11a. Type of Service |  |  | Turnkey | [6 empty] | 52109 | 0
BOM and Parts Procurement:
12.BOM received Date: | 2019-08-20 | [8 empty] | 15.SZ stock check: |  |  | No
13.Consigned Parts: | None | [8 empty] | 16.Authoriz Code: |  |  | 56151_M10823
14.DNI Parts: | Item #: 10,11 | [8 empty] | 17.Parts procurement: |  |  | Vani |  |  | # of days required for Purchasing | [5 empty] | 3
17a. Procurement finish Date | 2019-08-26 | [8 empty] | 17b. Parts arrival in Toronto |  |  | 2019-08-27
Note: These days are not for rush orders
Special Assembly Requirements: | [9 empty] | 18.Assembly Process |  |  | Lead-free
A total of 130 Boards will be fabricated. 50 Boards are to use 64307A1_M1, 30 boards are to use 64307A1_T1, and 50 Boards are to use 64307A1_U1.
Please process as a rush order as the client has paid extra for it. Please fabricate all the boards by August 30th, parts should arrive by then.
Please assemble as soon as possible and send out by September 9th.
Process In Markham.
Refer To 64307A1_M1 Gerbers. They are the same.
19.Returning Parts: | None |  |  | 24.Conformal Coating: |  |  |  | No |  |  | 28.SMT Pads |  | 53
[11 empty] | 29. Holes |  | 10
20.Picture Approval: | Yes |  |  | 25.Programming: |  |  |  | No |  |  | 30. BOM Lines |  | 14
[11 empty] | 31. All Parts |  | 13
21.Functional Testing: | No |  |  | 26.Shipped by: |  |  |  | UPS/FedEx |  |  | 32. Double side |  | N
[11 empty] | 33. Leadfree |  | Y
22.Files Provided: | Gerber files, ProductionBOM | [9 empty] | 34. BGA/Fine Pitch |  | 0
[11 empty] | 35. Package |  | 0603
23.Parts for Approval: | None |  |  | 27. Balance Payment: |  |  |  | - |  |  | 37. BGA/QFN |  | 0 | 0 | 0
[11 empty] | 38. Fine Pitch |  | 0 | 0 | 0
PCB fab notes: |  | 1st order: |  | 30 | PCS |  |  |  | 2nd order: |  | 0 | PCS
Other requirements: Please process as a rush order as the client has paid extra for it. Please fabricate all the boards by August 30th, parts should arrive by then.
Please assemble as soon as possible and send out by September 9th. Refer To 64307A1_M1 Gerbers. They are the same.
Board Size: | 0.78 |  | inch | X | 1.18 | inch |  |  | Impedance Control: |  |  |  | NO
Panel Size: |  |  | inch | X |  | inch |  |  | Materials: |  |  | FR4(TG140)
Board Thickness: | 0.063 |  | inch | [5 empty] | No. of Layers: |  |  | 2
Legend Color: | White |  |  | 2 | Sides |  |  |  | Mask Color: |  |  | Green |  | 2 | Sides
Copper Weight: | Outer 1.0/1.0 oz |  |  | 0 |  |  |  |  | Electrical Testing: |  |  |  | YES
Panelization: |  |  |  | 1PNL | = |  | pcs. |  | Surface Finish: |  |  | Gold Immersion
Blind or Buried vias: |  | NO | [6 empty] | Gold finger: |  |  |  | NO
[9 empty] | Via on Pad: |  |  | NO